## Overview
PROJECT: CROSS-FUNCTIONAL REVENUE OPERATIONS TRANSFORMATION — AROMA
Project ID | AROMA-REVOPS-2020 | Sponsor | CEO (chairs results-review meetings)
Project Lead (PM) | Thuy Van — COO (me) | Technology team | Tuấn Vũ · Trà Giang
Start date | 2020-01-06 | Core project close | 2021-06-30
Post-project optimization | Jun 2021 – Aug 2022 (data optimization tail; BI report v1 = Aug 2022)
Functions involved | Marketing · Telesales · Sales · Training · Accounting | Geographic scope | Multi-branch (Hanoi & HCMC)
Platform | In-house no-code/low-code (issue-based: workflow, automation, JQL, sync) | Project type | RevOps operational transformation
PROJECT OBJECTIVES
1. Standardize a single customer process across all branches.
2. Digitize the full Lead-to-Cash funnel so every lead & transaction leaves a data trail.
3. Make stage-by-stage conversion measurable to optimize the funnel.
4. Enable revenue attribution to content creator, ad operator, telesales rep, and closer.
5. Eliminate data waste via automated routing, recall, and recycling of un-closed leads.
6. Wire compensation directly to operational data, with fair per-stage allocation.
7. Provide near-real-time cross-functional BI reporting to leadership.
PROGRESS DASHBOARD (auto from 'WBS & Tasks')
Metric | Value | Metric | Value
Total tasks | 26 | Avg % complete | 100%
Completed | 26 | In progress | 0
Not started | 0 | On hold | 0

## Team & Participants
PROJECT TEAM & PARTICIPANTS
Role | Name | Function | Involvement | Key responsibilities
Sponsor / Executive | CEO | Executive Board | Sponsor · chairs results-review meetings | Approves direction; reviews outcomes in periodic results meetings; removes blockers
Project Lead (COO) | Thùy Vân (me) | Operations / Executive | Owner · architect · delivery lead | Designs the full RevOps system (process, data model, attribution, compensation); leads cross-functional rollout & change management
Technology (1) | Tuấn Vũ | Technology | Core contributor | System configuration: workflow, automation, cross-object sync, recall/recycle engine
Technology (2) | Trà Giang | Technology | Core contributor | Project/workflow setup; lead-routing engine; receipt & revenue configuration
Marketing Lead | Huyền Mai | Marketing | Contributor | Lead generation; UTM/attribution inputs; campaign source setup
Telesales Lead | Hiền Nguyễn | Telesales | Contributor | First-touch qualification; appointment booking; telesales process adoption
Sales Lead — HN (Cầu Giấy) | Hoàng Tuyết | Sales | Contributor (pilot & HN rollout) | HN branches incl. pilot; sales-process feedback; staff training on the new process
Sales Lead — HCM | Phan Thơm | Sales | Contributor (HCM rollout) | HCM branches; sales-process adoption & staff training
Accounting Lead | Thu Thủy | Accounting | Contributor | Receipts; revenue recognition; compensation calculation inputs
Training Lead | Thùy Vân (COO — kiêm nhiệm) | Training | Contributor (COO also leads Training) | Trial teaching/assessment; renewal (re-sell) motion
Note: names in [brackets] are role placeholders — replace with the actual person. 'Thuy Van (me)' = project owner/COO.

## Current-State
CURRENT-STATE ASSESSMENT
ID | Problem area | Current state (issue) | Business impact | Root cause | Severity | Resolution direction
CS-01 | Process | Each branch ran a different process; leadership lacked real-site visibility | No control, no cross-branch comparison | Lack of standardization & operational governance | High | Standardize one process, enforced through the system
CS-02 | People | Branch managers wanted autonomy, resisted oversight, externalized blame | Blocked change adoption | Legacy operating culture, low data transparency | High | Re-scope roles; pilot first; manage change psychology
CS-03 | Sales funnel | Appointment/contact rate only ~12-13% | Major funnel leak at intake | Telesales lacked process/pressure; low talk time (0.6-0.9h) | High | Standardize telesales process, lead scoring, data-driven bonus
CS-04 | Sales funnel | No stage-by-stage conversion measurement (MKT→appt→action→payment) | Couldn't locate where the funnel leaked | Fragmented, disconnected data | High | Digitize full funnel; enforce complete fields per stage
CS-05 | Data | 10-20% of leads unworked; qualified prospects lost | Lost potential revenue | No lead rotation / continuous nurturing | High | Round-robin routing + automated recall/recycle
CS-06 | Data | Reps hoarded personal pipelines; no rotation | Data 'died' in personal accounts | No data-ownership standard | Medium | Define data as company asset; recall after 3 months un-closed
CS-07 | Compensation | Couldn't trace lead source or who did which stage | Unfair incentives, low motivation | No attribution model or per-stage data | High | UTM attribution + multi-touch allocation; acquisition credit
CS-08 | Reporting | Disconnected Excel reports, per-branch templates, slow consolidation | Delayed executive decisions | No standardized data foundation or BI | Medium | Standard reporting framework + cross-functional BI dashboards

## WBS & Tasks
WORK BREAKDOWN STRUCTURE & TASK TRACKER
WBS | Task | Assignee | Participants | Start | Finish | Days | Status | % Complete | Depends | Notes
1 | P1. Diagnosis & Initiation
1.1 | Survey current-state operations per branch | Thùy Vân (COO — me) | Hiền Nguyễn, Hoàng Tuyết, Phan Thơm | 2020-01-06 | 2020-01-13 | 7 | Completed | 100% |  | Interviews + funnel data collection
1.2 | Analyze funnel leakage & bottlenecks | Thùy Vân (COO — me) |  | 2020-01-13 | 2020-01-20 | 7 | Completed | 100% | 1.1 | Appointment/action stage = key focus
1.3 | Confirm project objectives & scope | Thùy Vân (COO — me) | [CEO] | 2020-01-15 | 2020-01-22 | 7 | Completed | 100% | 1.2 | Charter reviewed with CEO
2 | P2. Process & Data Design
2.1 | Design Lead-to-Cash pipeline & state workflow | Thùy Vân (COO — me) | Tuấn Vũ, Trà Giang | 2020-01-20 | 2020-02-10 | 21 | Completed | 100% | 1.3 | 8 Deal states + Appointment workflow
2.2 | Design multi-object data model | Thùy Vân (COO — me) | Trà Giang (Tech) | 2020-01-27 | 2020-02-17 | 21 | Completed | 100% | 2.1 | Deal↔Appt↔Contact↔Receipt↔Customer
2.3 | Define field taxonomy | Thùy Vân (COO — me) | Huyền Mai, Thu Thủy | 2020-02-03 | 2020-02-20 | 17 | Completed | 100% | 2.2 | Attribution, source, status fields
2.4 | Design lead-scoring framework (5-criteria ABCD) | Thùy Vân (COO — me) | Hiền Nguyễn, Hoàng Tuyết, Phan Thơm | 2020-02-10 | 2020-02-24 | 14 | Completed | 100% | 2.3 | Need/Product/Finance/Location/Timing
3 | P3. System Configuration
3.1 | Create project cluster (CRM, Appt, Receipt, Revenue, Class) | Trà Giang (Tech) | Tuấn Vũ (Tech) | 2020-02-20 | 2020-03-05 | 14 | Completed | 100% | 2.2 | Partitioned by region
3.2 | Configure workflow, screens, fields, permissions | Tuấn Vũ (Tech) | Trà Giang (Tech) | 2020-02-24 | 2020-03-10 | 15 | Completed | 100% | 3.1 | Validators enforce fields per stage
3.3 | Automation & cross-object sync | Tuấn Vũ (Tech) | Trà Giang (Tech) | 2020-02-29 | 2020-03-15 | 15 | Completed | 100% | 3.2 | Deal→Contact→Receipt auto-generation
3.4 | Lead-routing engine (weighted round-robin) + accept status | Trà Giang (Tech) | Tuấn Vũ, Hiền Nguyễn | 2020-03-01 | 2020-03-20 | 19 | Completed | 100% | 3.3 | JQL filters by lead source
3.5 | Data recall & recycling on schedule | Tuấn Vũ (Tech) | Thùy Vân (COO — me) | 2020-03-10 | 2020-03-31 | 21 | Completed | 100% | 3.4 | Recall >3 months; block rotation
4 | P4. Attribution & Compensation
4.1 | Standardize UTM & attribution fields (locked) | Thùy Vân (COO — me) | Huyền Mai, Tuấn Vũ | 2020-03-01 | 2020-03-15 | 14 | Completed | 100% | 3.3 | utm_* + content/ad custom fields
4.2 | Design time-decay attribution model | Thùy Vân (COO — me) |  | 2020-03-10 | 2020-03-25 | 15 | Completed | 100% | 4.1 | 0-3m 100% / 3-6m 60% / 6-12m 30%
4.3 | Design per-stage revenue allocation | Thùy Vân (COO — me) | Hiền Nguyễn, Hoàng Tuyết, Phan Thơm | 2020-03-15 | 2020-03-31 | 16 | Completed | 100% | 4.2 | Tele 50% / Close 50%; acquisition separate
4.4 | Build bonus formula + quality-adjustment coefficient | Thùy Vân (COO — me) | Thu Thủy (Accounting Lead) | 2020-03-20 | 2020-04-15 | 26 | Completed | 100% | 4.3 | 4 salary tiers; ABCD coeff; manager override
5 | P5. Pilot
5.1 | Trial the new process on a test project | Tuấn Vũ (Tech) | Thùy Vân, Huyền Mai | 2020-03-28 | 2020-04-10 | 13 | Completed | 100% | 3.5 | MKT data push + sales process test
5.2 | Pilot rollout at one branch (Hoang Cau) | Thùy Vân (COO — me) | Hoàng Tuyết | 2020-04-01 | 2020-05-15 | 44 | Completed | 100% | 5.1 | Prove at one site first
5.3 | Train staff & refine process | Thùy Vân (COO — me) | Hoàng Tuyết | 2020-04-15 | 2020-05-31 | 46 | Completed | 100% | 5.2 | Onboard new staff to standard process
6 | P6. Cross-Branch Rollout
6.1 | Roll out to Hanoi branches | Thùy Vân (COO — me) | Hoàng Tuyết | 2020-06-01 | 2020-10-31 | 152 | Completed | 100% | 5.3 | Cau Giay, Hoang Cau...
6.2 | Roll out to HCMC branches | Thùy Vân (COO — me) | Phan Thơm | 2020-09-01 | 2021-03-31 | 211 | Completed | 100% | 6.1 | Region-split projects/accounts
6.3 | Standardize periodic staffing/ops reporting | Thùy Vân (COO — me) | Hiền Nguyễn, Hoàng Tuyết, Phan Thơm | 2020-07-01 | 2021-05-31 | 334 | Completed | 100% | 6.1 | Continuous reporting to managers & reps
7 | P7. Reporting Framework & Handover
7.1 | Design standard reporting framework ('aroma way') | Thùy Vân (COO — me) | [CEO] | 2021-01-01 | 2021-04-30 | 119 | Completed | 100% | 6.3 | Situation→issues→assessment→solution
7.2 | Documentation & handover; project close | Thùy Vân (COO — me) | Tuấn Vũ, Trà Giang | 2021-05-01 | 2021-06-30 | 60 | Completed | 100% | 7.1 | Core project completion (Q2 2021)
8 | P8. Post-Project Data Optimization
8.1 | Ongoing data optimization & cleanup | Thùy Vân (COO — me) | Tuấn Vũ, Trà Giang | 2021-06-01 | 2022-08-31 | 456 | Completed | 100% | 7.2 | Post-project; not part of core delivery
8.2 | Build cross-functional BI report v1 | Thùy Vân (COO — me) | [CEO] | 2022-01-01 | 2022-08-31 | 242 | Completed | 100% | 8.1 | Reviewed with CEO in results meeting; v1 = Aug 2022

## Milestones
PROJECT MILESTONES
ID | Milestone | Phase | Owner | Target date | Actual date | Status | Notes
M1 | Diagnosis complete & scope confirmed | P1 | Thùy Vân (COO — me) | 2020-01-22 | 2020-01-22 | Completed | Charter reviewed with CEO
M2 | Process & data model design signed off | P2 | Thùy Vân (COO — me) | 2020-02-24 | 2020-02-26 | Completed | 2-day slip
M3 | System configured, ready for pilot | P3 | Tuấn Vũ (Tech) | 2020-03-31 | 2020-04-02 | Completed
M4 | Attribution & compensation approved | P4 | Thùy Vân (COO — me) | 2020-04-15 | 2020-04-15 | Completed
M5 | Successful pilot at one branch | P5 | Thùy Vân (COO — me) | 2020-05-31 | 2020-05-31 | Completed | Hoang Cau branch
M6 | Rollout complete across HN & HCMC | P6 | Thùy Vân (COO — me) | 2021-03-31 | 2021-04-15 | Completed | HCMC slipped slightly
M7 | Reporting framework, handover — PROJECT CLOSE | P7 | Thùy Vân (COO — me) | 2021-06-30 | 2021-06-30 | Completed | Core project close (Q2 2021)
M8 | BI report v1 (post-project optimization snapshot) | P8 | Thùy Vân (COO — me) | 2022-08-31 | 2022-08-31 | Completed | Reviewed with CEO; downstream evidence, not a project deliverable

## KPIs
KEY PERFORMANCE INDICATORS (BASELINE — TARGET — ACHIEVED)
ID | KPI | Unit | Baseline | Target | Stabilized | Peak | Delta (pp) | Relative gain | Source / Notes
K1 | Appointment rate / MKT leads | % | 13% | 20% | 20% | 30% | 7% | 53.85% | Baseline from 2019-2020 funnel; ~30% at peak
K2 | Close rate (closed / actioned) | % | 36% | 50% | 50% | 67% | 14% | 38.89% | Matches BI report 08/2022 (~50%, up to ~67% by segment/period)
K3 | Unworked-lead rate | % | 15% | 5% | 5% | 3% | -10% | -66.67% | Baseline 10-20%; cut via auto routing & recall
K4 | Telesales talk time | hrs/day | 0.75 | 2 | 1.8 | 2.2 | 1.05 | 140% | Baseline 0.6-0.9h; up via process & quota pressure
K5 | Report consolidation time | days | 7 | 1 | 1 | 1 | -6 | -85.71% | From several days → near real-time via cross-functional BI

## Risks & Issues
RISK & ISSUE REGISTER
ID | Risk / Issue | Category | Likelihood | Impact | Severity | Mitigation | Owner | Status
R1 | Change resistance from branch managers | People | High | High | High | Re-scope roles; pilot first; manage psychology; transparent reporting | Thùy Vân (COO — me) | Resolved
R2 | Incomplete data entry by staff | Operations | High | High | High | Validators per stage; locked attribution fields; auto-fill | Tuấn Vũ (Tech) | Resolved
R3 | Unfair comp when a customer passes many hands | Compensation | Medium | High | High | Durable Contact model + time-decay attribution | Thùy Vân (COO — me) | Resolved
R4 | Wasted historical lead data | Data | High | Medium | Medium | Scheduled recall/recycle engine; re-warm before redistribution | Thùy Vân (COO — me) | Resolved
R5 | Technical risk in multi-object sync | Technical | Medium | High | High | Test on staging project; monitor automation; manual fallback | Trà Giang (Tech) | Monitoring
R6 | Dependency on key personnel in operations | Organization | Medium | Medium | Medium | Documented process; embed logic in system; succession training | Thùy Vân (COO — me) | Mitigated
R7 | External context affecting 2020 revenue | External | High | High | High | Focus on conversion optimization & data recycling to offset intake | Thùy Vân (COO — me) | Mitigated